## Slide 1: CDBG Closeouts
Tonika Prince
334-353-5353 tonika.prince@adeca.alabama.gov

## Slide 2: Closeout Introduction
Closeout verifies that CDBG funds have been properly spent and that the city/county complied with all requirements in completing its program.
The timeliness of closeout and the content of the information presented may be a factor for the evaluation of future CDBG applications.
There are thresholds every year that determine eligibility:
There can’t be more than one competitive grant open at a time.
Economic Development and Planning grants that are 3 years old can make a community ineligible.
Therefore, be sure to closeout in a timely manner.

## Slide 3: Grantee Responsibilities
Your responsibility is to effectively and efficiently manage and close out your CDBG program.
Closeout is initiated when:
  Final inspection of your last construction contract takes place (public works).
  Beneficiaries are in place (jobs).
  When the project is ready for closeout, download the CDBG Closeout Checklist from the CDBG website to use as a guide.

## Slide 4: Grantee Responsibilities
Closeout documents are due to the ADECA by the date indicated in your most recently approved “Implementation Schedule”. Please revise the closeout submittal date throughout the grant period to prevent possible loss of funds.
If your program has any unresolved / un-cleared findings from the ADECA monitoring visit(s), clear them prior to closeout.
The Closeout package should contain all required documents that coincide with the CDBG Checklist,

## Slide 5: Closeout Documents
Final Summary Change Order, Final Inspection(s), and As-Built Certification for projects with construction plans
Newspaper Advertisements for Notice of Completion
Final Wage Compliance Report
Final Disclosure Statement of all CDBG funds spent
FHEO report(s) (Sec 3 and Minority Contracting)
Closeout Public Hearing documents
List of Applicants and/or Hook-Up Certifications (If applicable)
Performance Assessment Report (pgs 1-4, 5 &6 if applicable)
Project Narrative and color images of Project Construction
Final CDBG Payment Request/Financial Expenditure
Audit Certification Form
All of these documents MUST be included in the Closeout package!
If one of these documents was previously submitted, note it on your cover letter and send a copy of the document in the Closeout package.

## Slide 6: Final Summary Change Order Final Inspection & As-Built Certification
Final Summary Change Order is obtained from the Engineer for final contract costs.
Final Inspection(s) ensures the work has been completed satisfactorily and in conformance with plans, specifications, and contract conditions. If your grant program involves more than one prime construction contract, complete and retain all “Final Inspection Certifications” and file all at closeout.
As-Built Certification confirms that the project was constructed as to the Engineer’s specifications.
Note: These are not required for Housing Rehabilitation projects or Planning grants.

## Slide 7: Newspaper Advertisement for Notice of Completion
Include the “Affidavit of Publication” from the newspaper and a published copy of the “Notice of Completion”.
  The ad must run once a week for three consecutive weeks.
  Final payment to the contractor is not made until 30 days after the date of the final ad.
  Contracts for less than $100,000 have different rules.
  The date of the first ad must not have been prior to the date of the “Final Inspection Certification”.
If a newspaper is not published in your area:
  Notice may be posted in a minimum of three (3) public places.
  It MUST be posted in the project area.
  It must be posted 30 days at the county courthouse, and proof of same shall be made by the judge of probate / sheriff, and the contractor.

## Slide 8: Final Wage Compliance Report and Final Disclosure Report
After approval of all final payrolls, complete the “Final Wage Compliance Report”.
  Submit all reports to your ADECA Program Manager at closeout.
  The Davis Bacon Act requires a “Final Wage Compliance Report” to be completed on each construction contract. Please be sure to include any and all restitution.
Final Disclosure Report to be completed once all CDBG funds are expended.
  Report only CDBG monies.
  Report final amounts and do not include any monies to be de-obligated.

## Slide 9: Minority Contracting Reports and Section 3
FINAL Form 2516 (Contract and Subcontract Report): Required for ALL grants (please see FH&EO specialist for questions).
FINAL Form 60002 (Section 3 Summary Report): Required for ALL grants (please see Section 3 Specialist for questions).
Final submittals of both forms are due at closeout with reporting of CDBG dollars only during the reporting period, including Planning Grants.

## Slide 10: Close Out Public Hearing Documentation
Provide the “Affidavit of Publication” for the advertisement for the public hearing and a published copy of the advertisement.
If a newspaper is not published in your area:
  Notice may be posted in a minimum of three (3) public places.
  It MUST be posted in the project area.
  Same advertising rules apply – proof of posting must be provided.
Submit the minutes and a roster of attendees from the hearing.
  The project must be discussed, even if there are no attendants from the public.
NOTE: Hearing should not be held prior to the date on the “Final Inspection Certification”.

## Slide 11: Assisted Forms and Certifications
List of Applicants Form (Housing Rehabilitation / Economic Development Projects Only)
  Include support documents (if necessary).
  For Housing Rehab, also include the Households Assisted Form.
  Is the beneficiary number consistent with the application or latest amendment?
Hook-up Certification (Water & Sewer projects only)
  Executed by the chief elected official (if hookups were included application)
  Hookups must be performed by a licensed plumber.
  Include Service Refusal Forms (if applicable).
  Are hook-up refusals included in the beneficiary number and consistent with the application or latest amendment?

## Slide 12
Make sure all forms are complete and accurate:
  Cover Sheet – signed by chief elected official
  Direct Benefit Activity Sheet – has anything changed?
  Performance Measures Summary Sheet (pages 3-6)
  Pages 5 & 6 only have to be included for Housing / Economic Development projects.
Check beneficiaries:
  Verify the final Beneficiary Table is correct.
  Is the beneficiary number consistent with the original application or latest amendment?
  If the beneficiary number differs more than 10% from the original application then immediately contact your CDBG Program Manager, because this might trigger an amendment that must be done before Close Out.
Performance Assessment Report

## Slide 13: Project Narrative and Photographs
Include a brief narrative (1/2 to full page) description of project accomplishments.
Submit color printed photos of project area / beneficiaries during and after construction.

## Slide 14
CDBG Final Expenditure Form

## Slide 15: CDBG Final Expenditure/ Payment Request
Prepare the “Final Expenditure”.
  Indicate total incurred cost. – Column 1
  Uses figures from “Last Approved Budget”. – Column 2 & 5
  Mark as “Final Expenditure” and indicate. – Column 3 &6
  Note any de-obligated funds in parentheses or added funds. Column 3 &6 (De-obligated funds are done by line item.)
Send request for payment of 10% administrative retainage (if applicable) and any other remaining funds.
Note that Final Request for Payment might be held until project is successfully closed, so be sure closeout package is complete.

## Slide 16: Audit Certification Form
This must be included with the proper block checked, and the form must be signed by the chief elected official.

## Slide 17
Common Problems or Deficiencies
Due to CDBG no later than MARCH 31, 2024 (not postmark date)
Required documents not received by DEADLINE.
Final Inspection not signed by appropriate representative(s).
“Notice of Completion” is not published/posted as required.
Forms/documents are incomplete or incorrectly prepared.
“Performance Assessment Report” is incomplete, late, or not adequately prepared.
Monitoring findings have not been addressed or cleared prior to close out.
Final Expenditure does not match final funds or Final Summary Change Order does not match construction cost.
Sam.gov registration is out of date.

## Slide 18
Questions?
Contact your CDBG Program Manager if you have any question or need further clarification.